## Sheet1
PO_ID | Department | Supplier_Name | Material_Category | Purchase_Request_Date | Manager_Approval_Date | RFQ_Sent_Date | Quotation_Received_Date | PO_Creation_Date | Supplier_Dispatch_Date | Material_Received_Date | Quality_Inspection_Date | Material_Released_Date | Procurement_Lead_Time_Days | Supplier_On_Time | Approval_Time_Days | Delivery_Delay_Days | Purchase_Order_Value | Procurement_Status | Risk_Level
PO001 | Production | Alpha Industrial Supplies | Raw Materials | 2026-01-01 | 2026-01-04 | 2026-01-05 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 16 | Yes | 3 | 1 | 850000 | Completed | Low
PO002 | Engineering | Techno Components | Electronics | 2026-01-02 | 2026-01-08 | 2026-01-09 | 2026-01-13 | 2026-01-14 | 2026-01-18 | 2026-01-23 | 2026-01-25 | 2026-01-26 | 24 | No | 6 | 5 | 620000 | Delayed | High
PO003 | Warehouse | Prime Logistics | Packaging | 2026-01-03 | 2026-01-05 | 2026-01-06 | 2026-01-08 | 2026-01-09 | 2026-01-11 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 12 | Yes | 2 | 0 | 300000 | Completed | Low
PO004 | Quality | Metro Suppliers | Testing Equipment | 2026-01-05 | 2026-01-10 | 2026-01-11 | 2026-01-15 | 2026-01-16 | 2026-01-22 | 2026-01-28 | 2026-01-30 | 2026-01-31 | 26 | No | 5 | 6 | 950000 | Delayed | High
PO005 | Operations | Green Materials | Raw Materials | 2026-01-06 | 2026-01-09 | 2026-01-10 | 2026-01-12 | 2026-01-13 | 2026-01-17 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 16 | Yes | 3 | 2 | 750000 | Completed | Medium
PO006 | Maintenance | Future Industries | Machinery | 2026-01-07 | 2026-01-15 | 2026-01-16 | 2026-01-21 | 2026-01-22 | 2026-01-28 | 2026-02-04 | 2026-02-06 | 2026-02-07 | 31 | No | 8 | 7 | 1250000 | Delayed | High
PO007 | R&D | Innovation Tech | Electronics | 2026-01-08 | 2026-01-10 | 2026-01-11 | 2026-01-14 | 2026-01-15 | 2026-01-18 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 15 | Yes | 2 | 1 | 540000 | Completed | Low
PO008 | Administration | Office Pro | Office Supplies | 2026-01-10 | 2026-01-12 | 2026-01-13 | 2026-01-15 | 2026-01-16 | 2026-01-19 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 14 | Yes | 2 | 0 | 180000 | Completed | Low
PO009 | Production | Alpha Industrial Supplies | Raw Materials | 2026-01-12 | 2026-01-18 | 2026-01-19 | 2026-01-22 | 2026-01-23 | 2026-01-28 | 2026-02-02 | 2026-02-04 | 2026-02-05 | 24 | No | 6 | 5 | 920000 | Delayed | High
PO010 | Engineering | Techno Components | Electronics | 2026-01-14 | 2026-01-17 | 2026-01-18 | 2026-01-21 | 2026-01-22 | 2026-01-25 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 16 | Yes | 3 | 1 | 680000 | Completed | Medium
PO011 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-01-15 | 2026-01-19 | 2026-01-20 | 2026-01-23 | 2026-01-24 | 2026-01-28 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 19 | No | 4 | 3 | 430000 | Delayed | Medium
PO012 | Quality | Prime Logistics | Packaging | 2026-01-17 | 2026-01-19 | 2026-01-20 | 2026-01-22 | 2026-01-23 | 2026-01-25 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 12 | Yes | 2 | 0 | 260000 | Completed | Low
PO013 | Operations | Global Textiles | Consumables | 2026-01-20 | 2026-01-24 | 2026-01-25 | 2026-01-28 | 2026-01-29 | 2026-02-02 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 19 | No | 4 | 4 | 500000 | Delayed | Medium
PO014 | Maintenance | Future Industries | Machinery | 2026-01-22 | 2026-01-30 | 2026-01-31 | 2026-02-05 | 2026-02-06 | 2026-02-12 | 2026-02-18 | 2026-02-20 | 2026-02-21 | 30 | No | 8 | 6 | 1500000 | Delayed | High
PO015 | R&D | Innovation Tech | Electronics | 2026-01-25 | 2026-01-27 | 2026-01-28 | 2026-01-31 | 2026-02-01 | 2026-02-04 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 15 | Yes | 2 | 1 | 610000 | Completed | Low
PO016 | Administration | Office Pro | Office Supplies | 2026-01-27 | 2026-01-29 | 2026-01-30 | 2026-02-01 | 2026-02-02 | 2026-02-05 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 14 | Yes | 2 | 0 | 200000 | Completed | Low
PO017 | Production | Metro Suppliers | Raw Materials | 2026-02-01 | 2026-02-07 | 2026-02-08 | 2026-02-12 | 2026-02-13 | 2026-02-18 | 2026-02-24 | 2026-02-26 | 2026-02-27 | 26 | No | 6 | 6 | 980000 | Delayed | High
PO018 | Engineering | Techno Components | Electronics | 2026-02-03 | 2026-02-06 | 2026-02-07 | 2026-02-10 | 2026-02-11 | 2026-02-15 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 17 | Yes | 3 | 2 | 720000 | Completed | Medium
PO019 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-02-05 | 2026-02-09 | 2026-02-10 | 2026-02-14 | 2026-02-15 | 2026-02-20 | 2026-02-25 | 2026-02-27 | 2026-02-28 | 23 | No | 4 | 5 | 460000 | Delayed | Medium
PO020 | Quality | Prime Logistics | Packaging | 2026-02-07 | 2026-02-09 | 2026-02-10 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 13 | Yes | 2 | 0 | 310000 | Completed | Low
PO021 | Operations | Green Materials | Consumables | 2026-02-10 | 2026-02-14 | 2026-02-15 | 2026-02-19 | 2026-02-20 | 2026-02-25 | 2026-03-02 | 2026-03-04 | 2026-03-05 | 23 | No | 4 | 5 | 560000 | Delayed | Medium
PO022 | Maintenance | Future Industries | Machinery | 2026-02-12 | 2026-02-20 | 2026-02-21 | 2026-02-26 | 2026-02-27 | 2026-03-05 | 2026-03-12 | 2026-03-14 | 2026-03-15 | 31 | No | 8 | 7 | 1350000 | Delayed | High
PO023 | R&D | Innovation Tech | Electronics | 2026-02-15 | 2026-02-17 | 2026-02-18 | 2026-02-21 | 2026-02-22 | 2026-02-25 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 15 | Yes | 2 | 1 | 650000 | Completed | Low
PO024 | Administration | Office Pro | Office Supplies | 2026-02-18 | 2026-02-20 | 2026-02-21 | 2026-02-23 | 2026-02-24 | 2026-02-27 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 13 | Yes | 2 | 0 | 190000 | Completed | Low
PO025 | Production | Alpha Industrial Supplies | Raw Materials | 2026-02-20 | 2026-02-26 | 2026-02-27 | 2026-03-03 | 2026-03-04 | 2026-03-09 | 2026-03-15 | 2026-03-17 | 2026-03-18 | 26 | No | 6 | 6 | 1050000 | Delayed | High
PO026 | Engineering | Techno Components | Electronics | 2026-02-22 | 2026-02-25 | 2026-02-26 | 2026-03-01 | 2026-03-02 | 2026-03-05 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 16 | Yes | 3 | 1 | 760000 | Completed | Medium
PO027 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-02-25 | 29-02-2026 | 2026-03-01 | 2026-03-05 | 2026-03-06 | 2026-03-11 | 2026-03-16 | 2026-03-18 | 2026-03-19 | 22 | No | 4 | 5 | 480000 | Delayed | Medium
PO028 | Quality | Prime Logistics | Packaging | 2026-02-27 | 2026-03-01 | 2026-03-02 | 2026-03-04 | 2026-03-05 | 2026-03-08 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 13 | Yes | 2 | 0 | 330000 | Completed | Low
PO029 | Operations | Global Textiles | Consumables | 2026-03-01 | 2026-03-05 | 2026-03-06 | 2026-03-10 | 2026-03-11 | 2026-03-16 | 2026-03-21 | 2026-03-23 | 2026-03-24 | 23 | No | 4 | 5 | 590000 | Delayed | Medium
PO030 | Maintenance | Future Industries | Machinery | 2026-03-03 | 2026-03-11 | 2026-03-12 | 2026-03-17 | 2026-03-18 | 2026-03-24 | 2026-03-31 | 2026-04-02 | 2026-04-03 | 31 | No | 8 | 7 | 1450000 | Delayed | High
PO031 | R&D | Innovation Tech | Electronics | 2026-03-05 | 2026-03-07 | 2026-03-08 | 2026-03-11 | 2026-03-12 | 2026-03-15 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 15 | Yes | 2 | 1 | 690000 | Completed | Low
PO032 | Administration | Office Pro | Office Supplies | 2026-03-08 | 2026-03-10 | 2026-03-11 | 2026-03-13 | 2026-03-14 | 2026-03-17 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 14 | Yes | 2 | 0 | 210000 | Completed | Low
PO033 | Production | Alpha Industrial Supplies | Raw Materials | 2026-03-10 | 2026-03-17 | 2026-03-18 | 2026-03-22 | 2026-03-23 | 2026-03-29 | 2026-04-05 | 2026-04-07 | 2026-04-08 | 29 | No | 7 | 7 | 1120000 | Delayed | High
PO034 | Engineering | Techno Components | Electronics | 2026-03-12 | 2026-03-15 | 2026-03-16 | 2026-03-19 | 2026-03-20 | 2026-03-24 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 17 | Yes | 3 | 2 | 780000 | Completed | Medium
PO035 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-03-15 | 2026-03-19 | 2026-03-20 | 2026-03-24 | 2026-03-25 | 2026-03-30 | 2026-04-05 | 2026-04-07 | 2026-04-08 | 24 | No | 4 | 6 | 510000 | Delayed | Medium
PO036 | Quality | Prime Logistics | Packaging | 2026-03-18 | 2026-03-20 | 2026-03-21 | 2026-03-23 | 2026-03-24 | 2026-03-27 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 14 | Yes | 2 | 0 | 350000 | Completed | Low
PO037 | Operations | Green Materials | Consumables | 2026-03-20 | 2026-03-25 | 2026-03-26 | 2026-03-30 | 2026-03-31 | 2026-04-05 | 2026-04-11 | 2026-04-13 | 2026-04-14 | 25 | No | 5 | 6 | 620000 | Delayed | Medium
PO038 | Maintenance | Future Industries | Machinery | 2026-03-22 | 2026-03-30 | 2026-03-31 | 2026-04-05 | 2026-04-06 | 2026-04-13 | 2026-04-21 | 2026-04-23 | 2026-04-24 | 33 | No | 8 | 8 | 1550000 | Delayed | High
PO039 | R&D | Innovation Tech | Electronics | 2026-03-25 | 2026-03-27 | 2026-03-28 | 2026-03-31 | 2026-04-01 | 2026-04-04 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 15 | Yes | 2 | 1 | 720000 | Completed | Low
PO040 | Administration | Office Pro | Office Supplies | 2026-03-28 | 2026-03-30 | 2026-03-31 | 2026-04-02 | 2026-04-03 | 2026-04-06 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 14 | Yes | 2 | 0 | 230000 | Completed | Low
PO041 | Production | Metro Suppliers | Raw Materials | 2026-04-01 | 2026-04-08 | 2026-04-09 | 2026-04-13 | 2026-04-14 | 2026-04-20 | 2026-04-27 | 2026-04-29 | 2026-04-30 | 29 | No | 7 | 7 | 1180000 | Delayed | High
PO042 | Engineering | Techno Components | Electronics | 2026-04-03 | 2026-04-06 | 2026-04-07 | 2026-04-10 | 2026-04-11 | 2026-04-15 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 17 | Yes | 3 | 2 | 800000 | Completed | Medium
PO043 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-04-05 | 2026-04-09 | 2026-04-10 | 2026-04-14 | 2026-04-15 | 2026-04-20 | 2026-04-26 | 2026-04-28 | 2026-04-29 | 24 | No | 4 | 6 | 530000 | Delayed | Medium
PO044 | Quality | Prime Logistics | Packaging | 2026-04-08 | 2026-04-10 | 2026-04-11 | 2026-04-13 | 2026-04-14 | 2026-04-17 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 14 | Yes | 2 | 0 | 370000 | Completed | Low
PO045 | Operations | Global Textiles | Consumables | 2026-04-10 | 2026-04-15 | 2026-04-16 | 2026-04-20 | 2026-04-21 | 2026-04-26 | 2026-05-02 | 2026-05-04 | 2026-05-05 | 25 | No | 5 | 6 | 650000 | Delayed | Medium
PO046 | Maintenance | Future Industries | Machinery | 2026-04-12 | 2026-04-20 | 2026-04-21 | 2026-04-26 | 2026-04-27 | 2026-05-04 | 2026-05-12 | 2026-05-14 | 2026-05-15 | 33 | No | 8 | 8 | 1600000 | Delayed | High
PO047 | R&D | Innovation Tech | Electronics | 2026-04-15 | 2026-04-17 | 2026-04-18 | 2026-04-21 | 2026-04-22 | 2026-04-25 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 15 | Yes | 2 | 1 | 740000 | Completed | Low
PO048 | Administration | Office Pro | Office Supplies | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 14 | Yes | 2 | 0 | 240000 | Completed | Low
PO049 | Production | Alpha Industrial Supplies | Raw Materials | 2026-04-20 | 2026-04-27 | 2026-04-28 | 2026-05-02 | 2026-05-03 | 2026-05-09 | 2026-05-16 | 2026-05-18 | 2026-05-19 | 29 | No | 7 | 7 | 1220000 | Delayed | High
PO050 | Engineering | Techno Components | Electronics | 2026-04-22 | 2026-04-25 | 2026-04-26 | 2026-04-29 | 2026-04-30 | 2026-05-04 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 17 | Yes | 3 | 2 | 820000 | Completed | Medium
PO051 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-04-25 | 2026-04-29 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-10 | 2026-05-16 | 2026-05-18 | 2026-05-19 | 24 | No | 4 | 6 | 550000 | Delayed | Medium
PO052 | Quality | Prime Logistics | Packaging | 2026-04-28 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-05-04 | 2026-05-07 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 14 | Yes | 2 | 0 | 390000 | Completed | Low
PO053 | Operations | Green Materials | Consumables | 2026-05-01 | 2026-05-06 | 2026-05-07 | 2026-05-11 | 2026-05-12 | 2026-05-17 | 2026-05-23 | 2026-05-25 | 2026-05-26 | 25 | No | 5 | 6 | 680000 | Delayed | Medium
PO054 | Maintenance | Future Industries | Machinery | 2026-05-03 | 2026-05-11 | 2026-05-12 | 2026-05-17 | 2026-05-18 | 2026-05-25 | 2026-06-02 | 2026-06-04 | 2026-06-05 | 33 | No | 8 | 8 | 1650000 | Delayed | High
PO055 | R&D | Innovation Tech | Electronics | 2026-05-05 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-12 | 2026-05-15 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 15 | Yes | 2 | 1 | 760000 | Completed | Low
PO056 | Administration | Office Pro | Office Supplies | 2026-05-08 | 2026-05-10 | 2026-05-11 | 2026-05-13 | 2026-05-14 | 2026-05-17 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 14 | Yes | 2 | 0 | 260000 | Completed | Low
PO057 | Production | Metro Suppliers | Raw Materials | 2026-05-10 | 2026-05-17 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-29 | 2026-06-05 | 2026-06-07 | 2026-06-08 | 29 | No | 7 | 7 | 1260000 | Delayed | High
PO058 | Engineering | Techno Components | Electronics | 2026-05-12 | 2026-05-15 | 2026-05-16 | 2026-05-19 | 2026-05-20 | 2026-05-24 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 17 | Yes | 3 | 2 | 850000 | Completed | Medium
PO059 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-05-15 | 2026-05-19 | 2026-05-20 | 2026-05-24 | 2026-05-25 | 2026-05-30 | 2026-06-05 | 2026-06-07 | 2026-06-08 | 24 | No | 4 | 6 | 570000 | Delayed | Medium
PO060 | Quality | Prime Logistics | Packaging | 2026-05-18 | 2026-05-20 | 2026-05-21 | 2026-05-23 | 2026-05-24 | 2026-05-27 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 14 | Yes | 2 | 0 | 410000 | Completed | Low
PO061 | Operations | Global Textiles | Consumables | 2026-05-20 | 2026-05-25 | 2026-05-26 | 2026-05-30 | 2026-05-31 | 2026-06-05 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 25 | No | 5 | 6 | 700000 | Delayed | Medium
PO062 | Maintenance | Future Industries | Machinery | 2026-05-22 | 2026-05-30 | 2026-05-31 | 2026-06-05 | 2026-06-06 | 2026-06-13 | 2026-06-21 | 2026-06-23 | 2026-06-24 | 33 | No | 8 | 8 | 1700000 | Delayed | High
PO063 | R&D | Innovation Tech | Electronics | 2026-05-25 | 2026-05-27 | 2026-05-28 | 2026-05-31 | 2026-06-01 | 2026-06-04 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 15 | Yes | 2 | 1 | 780000 | Completed | Low
PO064 | Administration | Office Pro | Office Supplies | 2026-05-28 | 2026-05-30 | 2026-05-31 | 2026-06-02 | 2026-06-03 | 2026-06-06 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 14 | Yes | 2 | 0 | 280000 | Completed | Low
PO065 | Production | Alpha Industrial Supplies | Raw Materials | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-13 | 2026-06-14 | 2026-06-20 | 2026-06-27 | 2026-06-29 | 2026-06-30 | 29 | No | 7 | 7 | 1300000 | Delayed | High
PO066 | Engineering | Techno Components | Electronics | 2026-06-03 | 2026-06-06 | 2026-06-07 | 2026-06-10 | 2026-06-11 | 2026-06-15 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 17 | Yes | 3 | 2 | 870000 | Completed | Medium
PO067 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-06-05 | 2026-06-09 | 2026-06-10 | 2026-06-14 | 2026-06-15 | 2026-06-20 | 2026-06-26 | 2026-06-28 | 2026-06-29 | 24 | No | 4 | 6 | 600000 | Delayed | Medium
PO068 | Quality | Prime Logistics | Packaging | 2026-06-08 | 2026-06-10 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 2026-06-17 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 14 | Yes | 2 | 0 | 430000 | Completed | Low
PO069 | Operations | Green Materials | Consumables | 2026-06-10 | 2026-06-15 | 2026-06-16 | 2026-06-20 | 2026-06-21 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-05 | 25 | No | 5 | 6 | 720000 | Delayed | Medium
PO070 | Maintenance | Future Industries | Machinery | 2026-06-12 | 2026-06-20 | 2026-06-21 | 2026-06-26 | 2026-06-27 | 2026-07-04 | 2026-07-12 | 2026-07-14 | 2026-07-15 | 33 | No | 8 | 8 | 1750000 | Delayed | High
PO071 | R&D | Innovation Tech | Electronics | 2026-06-15 | 2026-06-17 | 2026-06-18 | 2026-06-21 | 2026-06-22 | 2026-06-25 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 15 | Yes | 2 | 1 | 800000 | Completed | Low
PO072 | Administration | Office Pro | Office Supplies | 2026-06-18 | 2026-06-20 | 2026-06-21 | 2026-06-23 | 2026-06-24 | 2026-06-27 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 14 | Yes | 2 | 0 | 300000 | Completed | Low
PO073 | Production | Metro Suppliers | Raw Materials | 2026-06-20 | 2026-06-27 | 2026-06-28 | 2026-07-02 | 2026-07-03 | 2026-07-09 | 2026-07-16 | 2026-07-18 | 2026-07-19 | 29 | No | 7 | 7 | 1350000 | Delayed | High
PO074 | Engineering | Techno Components | Electronics | 2026-06-22 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-07-04 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 17 | Yes | 3 | 2 | 900000 | Completed | Medium
PO075 | Warehouse | Rapid Manufacturing | Spare Parts | 2026-06-25 | 2026-06-29 | 2026-06-30 | 2026-07-04 | 2026-07-05 | 2026-07-10 | 2026-07-16 | 2026-07-18 | 2026-07-19 | 24 | No | 4 | 6 | 620000 | Delayed | Medium

## Analysis
Metric | Value
Total Purchase Orders | 75
Average Lead Time | 20.6533
Delayed Orders | 37
Average Approval Time | 4.04
Average Delivery Delay | 3.44
High Risk Orders | 20
Metric | Value
Delay Percentage | 0.49333
On Time Orders | 38
Average PO Value | 744400
Total Procurement Spend | 55830000
Area | Issue | Recommendation
Approval Process | Slow approval cycle | Digital approval workflow
Supplier Performance | Late deliveries | Supplier scorecard system
Risk Management | High risk orders | Supplier risk monitoring
Procurement Planning | Long lead time | Forecasting improvement